## Clarification Log
haha
Date | Question/Clarification Needed | Response/Decision | Status
2025-07-09 | What is the primary target market for the platform? | Targeting 100+ colleges, events, fests, hackathons, clubs, and startups. | Closed
2025-07-09 | How are leads ranked for outreach? | Leads are ranked based on order volume, frequency, and urgency. | Closed
2025-07-09 | What pre-bundled offers are suggested? | Example: 20 hoodies + 30 mugs for ₹12,000. | Closed
2025-07-09 | How many suppliers should be identified and where? | 5–10 printing vendors in Tirupur, Erode, Sivakasi. | Closed
2025-07-09 | What criteria are used to score suppliers? | Quality (print resolution), MOQ, speed, and pricing. | Closed
2025-07-09 | What tools are recommended for supplier stock updates? | Use simple tools like Google Sheets for integration. | Closed
2025-07-09 | Who creates mockups for orders? | Design students are assigned to create mockups. | Closed
2025-07-09 | Which logistics partners are suggested for order fulfillment? | Blue Dart, DTDC, and local couriers. | Closed
2025-07-09 | Is there a client portal for order tracking and design approval? | Yes, an order tracking and visual design approval portal is included. | Closed
2025-07-09 | What is the monetization model for the platform? | 20–40% markup on print cost; white-label for college/university stores. | Closed
2025-07-08 | What's included in the initial launch? | Core ordering workflow only. Advanced features in Phase 2. | Closed
2025-07-08 | What's the project budget? | ₹12L total for MVP. | Closed
2025-07-08 | Key success metrics? | Quote conversion %, lead scores, vendor performance, profit margins. | Closed
2025-07-08 | How do we score leads? | 50% Volume + 30% Frequency + 20% Urgency (0-100 scale). | Closed
2025-07-08 | Where do we get customer data? | Import from existing CRM + new web form entries. | Closed
2025-07-08 | Do combo prices update automatically? | Yes, with dynamic 20-40% markup. | Pending
2025-07-08 | How many vendors to start with? | 6 vendors total (2 each in Tirupur, Erode, Sivakasi). | Closed
2025-07-08 | Quality standards? | Minimum 300 DPI print resolution + sample approval. | Closed
2025-07-08 | How often to update vendor pricing? | Weekly manual updates initially. | Pending
2025-07-08 | Design team size needed? | 5 design students on hourly basis. | Closed
2025-07-08 | Delivery partners? | Blue Dart (priority), DTDC (economy), Dunzo (local). | Closed
2025-07-08 | Order tracking milestones? | In Production → Dispatched → Delivered. | Pending
2025-07-08 | Pricing structure? | 40% markup <₹10k, 30% for ₹10-25k, 25% for ₹25-50k, 20% >₹50k. | Closed
2025-07-08 | Return policy timeframe? | 7 days from delivery for quality issues. | Pending
2025-07-08 | Who handles return costs? | 50-50 split between vendor and platform initially. | Pending